NASLA-Africa

Bemenda, Cameroon

ActivitiesTimeline

| ProjectActivities | Year 2025 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| Phase I |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity1:Hold Project incepting/stakeholder meeting | X |  |  |  |  |  |  |  |  |  |  |  |
| Activity2 and 3: Select and train beneficiaries (Returnees), distrubute basic supplies, seeds and tools |  | X |  |  |  |  |  |  |  |  |  |  |
| Phase II |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 4: Conduct Baseline on Household Income level of selected returnees |  |  | X |  |  |  |  |  |  |  |  |  |
| Activity 5 and 6: Purchase and install processing mills |  |  |  | x |  |  |  |  |  |  |  |  |
| Activity 7 and 8: Group selected returnees into 3 hubs or groups and elect executive members per Hub or group and train them |  |  |  | x | x |  |  |  |  |  |  |  |
| Activity 9: , conduct community widespread awareness generation over Rainbow community radio station (Mbengwi) on the availability of the mill hubs as a support from NASLA-Africa and its partners |  |  |  |  | x | x |  |  |  |  |  |  |
| Phase III |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 10: Conduct post operational monitoring and coaching |  |  |  |  |  |  | x |  |  |  |  |  |
| Activity 11: Conduct monthly joint supportive field supervision |  |  |  |  |  |  |  | x | x | x | X |  |
| Writing Final Report |  |  |  |  |  |  |  |  |  |  |  | X |
| Evaluation / end-line survey |  |  |  |  |  |  |  |  |  |  |  | X |

Page|1