THE TRUST FOR THE AMERICAS

Help 100 Latin American Entrepreneurs

Close the AI Gap

Project Budget & Cost-Share Plan

GlobalGiving Campaign  |  Program Period: 2026

| Total Program Cost | GlobalGiving Ask | Trust Cost-Share | Entrepreneurs Served |
| --- | --- | --- | --- |
| $122,285 | $50,000 | $72,285 | 100 |

| GlobalGiving Donor Funding covers 40.9% of total program cost | The Trust for the Americas provides 59.1% as institutional cost-share |
| --- | --- |

Executive Summary

This document presents the full budget for the AI Advisory Initiative — a program that will provide hands-on AI advisory support to 100 small business owners across Latin America. The budget is structured as a cost-share arrangement: GlobalGiving donors provide $50,000, and The Trust for the Americas contributes the remaining $72,285 through institutional resources, staff time, and in-kind support.

Budget figures are grounded in a real pilot program conducted by The Trust in the Dominican Republic (June–July 2026), which delivered AI advisory services to 5 medium-sized businesses at a fully-loaded cost of $19,160. Scaling that experience to 100 small businesses — which require approximately 60% of the advisory effort of a medium business — yields a total program cost of $122,285.

Cost-Share Structure

The Trust for the Americas is committed to this program as a core institutional priority. Our cost-share contribution reflects that commitment and includes:

- Staff time from salaried employees not charged to the grant

- Amortized equipment already purchased for the DR pilot (MacBook Pro M5 units, monitors)

- AI subscription tools that will be shared across multiple projects

- Organizational overhead, partner network management, and M&E capacity

- Travel for country visits where local partner relationships reduce unit costs

The $50,000 from GlobalGiving donors is essential and directly funds the variable, per-entrepreneur costs: AI advisor hours, diagnostic toolkits, session materials, peer network access, and targeted travel. Without donor funding, these direct service costs cannot be covered by institutional resources alone.

Full Program Budget — 100 Entrepreneurs

| ● GlobalGiving (donor funding) | ● Trust Cost-Share (institutional) |
| --- | --- |

1. Personnel

| Item / Description | Unit Cost | Qty / Hrs | Unit | Total ($) | GlobalGiving | Trust Cost-Share |
| --- | --- | --- | --- | --- | --- | --- |
| Lead AI Advisor (Program Lead) | $65/hr | 300 hrs | hours | $19,500 | — | $19,500 |
| AI Advisors (×2) | $50/hr | 400 hrs ea. | hours | $40,000 | $30,000 | $10,000 |
| Support Coordinator | $40/hr | 200 hrs | hours | $8,000 | $8,000 | — |
| Program Manager | $65/hr | 100 hrs | hours | $6,500 | — | $6,500 |
| M&E Officer | $45/hr | 60 hrs | hours | $2,700 | — | $2,700 |
| PERSONNEL SUBTOTAL |  |  |  |  |  | $76,700 |

Basis: DR pilot staffed 2 people for 140 hours at $7,513 for 5 medium businesses. Scaled to 100 small businesses (60% effort per engagement) with an expanded 4-person team over 6 months.

2. AI Subscription Tools

| Item / Description | Unit Cost | Qty / Hrs | Unit | Total ($) | GlobalGiving | Trust Cost-Share |
| --- | --- | --- | --- | --- | --- | --- |
| Claude Max 20x (4 users × 6 months) | $200/mo | 24 | user-months | $4,800 | $2,400 | $2,400 |
| ChatGPT Pro (4 users × 6 months) | $100/mo | 24 | user-months | $2,400 | $1,200 | $1,200 |
| Gemini Ultra (4 users × 6 months) | $100/mo | 24 | user-months | $2,400 | $1,200 | $1,200 |
| Extra usage, APIs & specialized tools | variable | 1 | lump sum | $1,600 | $800 | $800 |
| AI TOOLS SUBTOTAL |  |  |  |  |  | $11,200 |

Basis: DR pilot used Claude Max 20x, ChatGPT Pro, and Gemini Ultra at $1,300 for 6 weeks (2 users). Scaled to 4 users over 6 months with expanded API usage.

3. Equipment

| Item / Description | Unit Cost | Qty / Hrs | Unit | Total ($) | GlobalGiving | Trust Cost-Share |
| --- | --- | --- | --- | --- | --- | --- |
| 14" MacBook Pro M5 (Unit 1 — Washington D.C., 24GB/1TB) | — | 1 | unit | $2,013 | — | $2,013 |
| 14" MacBook Pro M5 (Unit 2 — Alabama, 24GB/1TB) | — | 1 | unit | $2,089 | — | $2,089 |
| OAS IT Management Solution (×2 MacBooks) | $360 | 2 | units | $720 | — | $720 |
| Portable Monitor 15.6" FHD w/Smart Cover (×2) | $55 | 2 | units | $110 | — | $110 |
| EQUIPMENT SUBTOTAL |  |  |  |  |  | $4,932 |

Note: Equipment already purchased for the DR pilot; costs reflected here as institutional cost-share contribution (amortized). No donor funds are used for equipment.

4. Travel

| Item / Description | Unit Cost | Qty / Hrs | Unit | Total ($) | GlobalGiving | Trust Cost-Share |
| --- | --- | --- | --- | --- | --- | --- |
| Trip 1 — Dominican Republic: Roundtrip airfare (2 people) | $800 | 2 | tickets | $1,600 | $1,600 | — |
| Trip 1 — DR: Per diem (4 nights × 2 people) | $243 | 8 | nights | $1,944 | $1,944 | — |
| Trip 1 — DR: Internal transportation | $490 | 1 | lump sum | $490 | $490 | — |
| Trip 2 — Colombia/Mexico: Roundtrip airfare (2 people) | $900 | 2 | tickets | $1,800 | $1,800 | — |
| Trip 2 — Colombia/Mexico: Per diem (4 nights × 2) | $243 | 8 | nights | $1,944 | $944 | $1,000 |
| Trip 2 — Colombia/Mexico: Internal transportation | $400 | 1 | lump sum | $400 | — | $400 |
| Trip 3 — Central America: Roundtrip airfare (2 people) | $700 | 2 | tickets | $1,400 | — | $1,400 |
| Trip 3 — Central America: Per diem (3 nights × 2) | $243 | 6 | nights | $1,458 | — | $1,458 |
| Trip 3 — Central America: Internal transportation | $300 | 1 | lump sum | $300 | — | $300 |
| TRAVEL SUBTOTAL |  |  |  |  |  | $11,336 |

5. Program Materials & Delivery

| Item / Description | Unit Cost | Qty / Hrs | Unit | Total ($) | GlobalGiving | Trust Cost-Share |
| --- | --- | --- | --- | --- | --- | --- |
| AI Readiness Diagnostic Toolkits (100 entrepreneurs) | $25 | 100 | businesses | $2,500 | $2,500 | — |
| Session workbooks & learning resources | $10 | 100 | businesses | $1,000 | $1,000 | — |
| Peer network platform (6-month license) | $250/mo | 6 | months | $1,500 | $1,500 | — |
| Outreach, comms & beneficiary recruitment | variable | 1 | lump sum | $2,000 | — | $2,000 |
| MATERIALS SUBTOTAL |  |  |  |  |  | $7,000 |

6. Contingency (10%)

| Item / Description | Unit Cost | Qty / Hrs | Unit | Total ($) | GlobalGiving | Trust Cost-Share |
| --- | --- | --- | --- | --- | --- | --- |
| Contingency reserve @ 10% of direct costs | 10% | 1 | lump sum | $11,117 | $5,556 | $5,561 |
| CONTINGENCY SUBTOTAL |  |  |  |  |  | $11,117 |

Budget Summary

| Budget Category | Total Cost | % of Total | GlobalGiving | Trust Cost-Share |
| --- | --- | --- | --- | --- |
| 1. Personnel | $76,700 | 62.7% | $38,000 | $38,700 |
| 2. AI Subscription Tools | $11,200 | 9.2% | $5,600 | $5,600 |
| 3. Equipment | $4,932 | 4.0% | — | $4,932 |
| 4. Travel | $11,336 | 9.3% | $6,778 | $4,558 |
| 5. Program Materials & Delivery | $7,000 | 5.7% | $5,000 | $2,000 |
| 6. Contingency (10%) | $11,117 | 9.1% | $5,556 | $5,561 |
| TOTAL PROGRAM BUDGET | $122,285 | 100% | $50,000 | $72,285 |
| Share of total program cost |  |  | 40.9% | 59.1% |

Methodological Note: Basis for Budget Projections

All budget figures are derived from an actual program pilot conducted by The Trust for the Americas in the Dominican Republic (June 1 – July 17, 2026). The pilot delivered AI advisory services to 5 medium-sized businesses with the following actuals:

| DR Pilot Category | Actual Cost | Businesses Served |
| --- | --- | --- |
| Personnel | $7,513 | 5 medium businesses |
| AI Subscription Tools | $1,300 | 5 medium businesses |
| Equipment | $4,572 | One-time investment |
| Travel (Dominican Republic) | $4,034 | 1 country trip |
| Contingency (10%) | $1,742 | — |
| PILOT TOTAL | $19,161 | 5 medium businesses |

Scaling assumptions applied to reach the full program budget for 100 small businesses:

- Small businesses require approximately 60% of the advisor time needed for medium businesses

- Team expanded from 2 to 4 staff to manage volume across multiple countries

- AI tool subscriptions scaled from 2 to 4 users and extended from 6 weeks to 6 months

- Equipment cost is institutional cost-share (already purchased); no new equipment budgeted

- Travel expanded to 3 country visits to reach entrepreneurs across the region

The Trust for the Americas  |  OAS Affiliate  |  Promoting Social and Economic Inclusion Since 1997  |  www.trustfortheamericas.org