| جمعيـة عمـل تنمـوي بـلا حـدود |  | Developmental Action Without Borders |
| --- | --- | --- |
| نبـــع |  | NABA’A |
| علم وخبر: 104/أد |  | Reg: 104\AD |

# Warm Hands, Hopeful Hearts

Winter Clothing and Shoes for 450 Displaced Children in South Lebanon

GLOBALGIVING PROJECT DOCUMENT  |  WINTER 2026–2027

# Project at a Glance

| Implementing organization | Developmental Action without Borders – Naba’a |
| --- | --- |
| Location | Tyre District and surrounding affected communities, South Lebanon |
| Primary beneficiaries | 450 vulnerable displaced children |
| Proposed duration | 3 months |
| Fundraising target | USD 27,000 |
| Estimated assistance cost | USD 60 per child |

# Project Summary

As winter approaches, displaced children in South Lebanon face harsh weather without adequate clothing or shoes. Conflict, displacement, and economic hardship have left families struggling to meet basic needs. Through Warm Hands, Hopeful Hearts, Naba’a aims to provide 450 vulnerable displaced children with warm clothing kits and winter shoes, helping them stay protected while restoring comfort, dignity, and hope.

# The Challenge

Prolonged conflict and repeated displacement in South Lebanon have damaged homes, disrupted livelihoods, and placed significant pressure on vulnerable families. In Tyre District, many families are staying in rented accommodation, with host families, or in collective settings while struggling to afford food, shelter, and healthcare. As winter approaches, children without suitable jackets, warm garments, and proper shoes face additional discomfort and exposure to cold and wet conditions.

# Our Response

Naba’a will identify and support 450 displaced children through its field presence, community networks, and coordination with local stakeholders. Priority will be given to severely economically vulnerable households, female-headed households, families with multiple children, and children with disabilities. Each child will receive a size-appropriate winter clothing kit and a pair of winter shoes, distributed free of charge in a safe, accessible, child-sensitive and dignified manner.

# Core Activities

Identify and verify children based on transparent vulnerability criteria and community outreach.

Procure and quality-check winter clothing kits (jacket, sweater, warm trousers, socks and winter accessories) and durable winter shoes.

Organize accessible distributions, verifying sizes and documenting assistance received.

Conduct post-distribution monitoring and collect caregiver feedback through accessible complaints and feedback channels.

# Expected Results

450 displaced children receive winter clothing kits.

450 displaced children receive a pair of winter shoes.

All selected children are intended to receive appropriately sized items.

At least 90% of surveyed caregivers report satisfaction with the assistance (project target).

# Proposed Budget (USD)

| Cost item | Quantity | Unit cost | Total |
| --- | --- | --- | --- |
| Winter clothing kits | 450 | $40 | $18,000 |
| Winter shoes | 450 | $15 | $6,750 |
| Packaging, transport and distribution | 450 | $5 | $2,250 |
| TOTAL |  |  | $27,000 |

Budget assumptions are indicative and should be confirmed through procurement quotations. The estimated complete package, including distribution, is $60 per child. Any platform fees or unlisted administrative costs would need to be addressed separately.

# Monitoring and Accountability

Naba’a will record distribution quantities, check size suitability, monitor caregiver satisfaction and document complaints or feedback. Beneficiary information will be handled confidentially, with safeguarding and child-sensitive distribution procedures throughout implementation.

# Why Support This Project?

A $60 donation can cover an estimated full winter clothing and shoe package for one displaced child. Supporting this project helps children face the cold with greater warmth and dignity while easing pressure on families already coping with displacement and financial hardship.